HUNGER.

— BETA SPRINT PLAN · V2

The lean path to a 200-user beta.

Funding follows traction. The near-term target isn’t launch — it’s a beta that earns the raise.

CONFIDENTIAL · FOR THE THREE CO-FOUNDERS · STARTUP MODE / PRE-RAISE

— WHY THIS PLAN LOOKS DIFFERENT

Two things changed the shape of this.

Because funding comes after we land roughly 200 beta users, the goal of this phase is narrow: ship a beta good enough to prove the worldview works, recruit 200 engaged people, and use that signal to open the raise. Everything that doesn’t serve that is deferred.

And because Matt is fast, the build is no longer the bottleneck. The critical path is now the decisions that unblock the build, and the slow external humans — a clinical advisor and 200 recruited users. Neither moves faster because the app does. We pace the plan to those, not to the code.

— THE ONE NON-NEGOTIABLE Clinical sign-off before any external beta user. Our beta cohort includes the recovering tracker by design. Putting someone with a disordered-eating history onto an AI that gives fueling and training advice, with no clinician having reviewed the refusal logic, is both a real harm and the screenshot that ends the brand. The lean version: a scoped, paid review — not a hire. Days of a clinician’s time to review FIG’s prompt, the intake floors, and the Guardian, and sign off before external beta. The build can move fast everywhere except the safety layer, which gets the careful pass regardless of velocity.

— RUN THEM CONCURRENTLY

Three co-founders. Three lanes.

This is an even three-way split, not a hierarchy. Each lane runs in parallel through every sprint; filter the board by lane and each of us sees only our own work. We are all co-founders — the labels below are focus areas, not rank.

| LANE | FOCUS AREA · CO-FOUNDER |
| --- | --- |
| BRAND & PRODUCT | Josh — co-founder, marketing, branding & product direction. Owns the worldview’s expression: FIG’s voice and refusal logic, the manifesto, all pre-raise growth, and beta recruitment. |
| ENGINEERING | Matt — co-founder, CTO. Owns the build: the core check-in loop, FIG integration, and the safety layer. Fast everywhere except the safety layer, which gets the careful pass. |
| BUSINESS & OPS | Thad — co-founder, business & ops. Owns trademark, the clinical advisor, lean legal, beta logistics, and raise prep. |

— THE PLAN

Three sprints to the milestone.

SPRINT 0  Lock & Unblock

WEEK 1   Decisions only. Nobody builds yet.

| CARD | LANE | DONE WHEN |
| --- | --- | --- |
| Resolve: does the app track numbers, or not? | BRAND + ENG BLOCKER | One written answer. Every screen matches it. Free decision that unblocks FIG, design, and legal. |
| Lock the beta MVP cut list | BRAND + ENG BLOCKER | An “in” and “out” list, both signed. No payments, no store, no full analytics in beta. |
| Close FIG model / cost / data decision | ENG BLOCKER | A per-user FIG cost figure exists for the raise model. |
| Confirm 3 lanes + decision rights (1 page) | ALL | Signed by all three, pinned to the board. |
| Open clinical advisor outreach — start day 1 | BIZ BLOCKER | Candidates contacted. This is the long pole; it starts first. |
| File trademark (background, not a beta gate) | BIZ | HUNGER + FIG filed in apparel and software classes. |
| Waitlist live + manifesto drafting begins | BRAND | Page capturing emails with a referral loop; first manifesto draft exists. |

SPRINT 1  Build & De-risk

WEEKS 2–4   All three lanes at once.

| CARD | LANE | DONE WHEN |
| --- | --- | --- |
| Build core loop: check-in + Verdict + Pattern | ENG | Tester gets a one-truth / one-action Verdict. Pattern shows relative bands — zero digits. |
| Build Guardian + intake floors (safety — don’t rush) | ENG BLOCKER | Under-fueling alert fires correctly AND the advisor has reviewed the wording. |
| FIG system prompt v1 (voice + refusal logic) | BRAND | Versioned prompt with explicit refusal cases for restriction. |
| Run the pre-raise growth motion (see Brand track) | BRAND | Manifesto public, creators seeded, waitlist climbing toward 200+. |
| Sign clinical advisor; advisor reviews FIG + Guardian | BIZ BLOCKER | Advisor contracted and has read the FIG prompt + Guardian spec. |
| Lean legal: ToS, privacy, 17+, AI disclaimer | BIZ | Drafts in place; AI-coach liability posture documented. |

SPRINT 2  Harden & Beta

WEEKS 5–7   Ship it — once it’s signed off.

| CARD | LANE | DONE WHEN |
| --- | --- | --- |
| Integrate FIG + internal QA | ENG | Full beta loop works end-to-end internally. |
| Red-team FIG + clinical sign-off (HARD GATE) | ENG + BIZ BLOCKER | Advisor signs off in writing that FIG is safe to ship to external users. |
| Recruit + confirm 200 beta users | BRAND BLOCKER | 200 confirmed from the waitlist, with access scheduled. |
| Beta logistics: TestFlight, onboarding, feedback | BIZ | Invite flow plus a way to capture retention and share behavior. |
| Ship closed beta to 200 | ALL BLOCKER | 200 users have access. Gated on clinical sign-off. |

— HOW THE 200 GET HERE — FOR FREE

Pre-raise growth, in one breath.

We can’t buy reach yet. Good — this brand was built to be repeated, not advertised. The full playbook lives in the Brand & Growth track doc; the motion in short:

- The manifesto is the product before the product — ship it as screenshot-bait on every surface.

- Seed ~30 aligned mid-tier creators with the manifesto and a shirt — gift the flag, don’t buy the post.

- Build in public — the build itself is the content, and it creates the founding cohort.

- Make the waitlist a status object with a referral loop — a free viral motion baked into signup.

- Go IRL in one city — run club, gym sticker drops, shirts on real backs at meets.

— MILESTONE · WEEK 7–8 Beta = raise trigger. 200 engaged users with retention data — not 200 installs. The raise is triggered by signal: people coming back, people screenshotting the Verdict. 200 installs at 15% week-two retention isn’t a raise, it’s a diagnosis. Build the beta to measure the worldview working, because that is the thing we are actually selling to partners.

Stay hungry.  Eat enough.

The brand is the rebellion. The product is the responsible adult underneath. The beta proves both.