HUNGER.

— BUSINESS & OPERATIONS TRACK · PRE-RAISE

Clear the path, then earn the raise.

Owner: Thad — co-founder, business & ops. Your job this phase: unblock the two slow things only you can move, keep the build legal and safe, and turn 200 beta users into a fundable story.

CONFIDENTIAL · CO-FOUNDER TRACK · IN LINE WITH BETA SPRINT PLAN V2

— YOUR MANDATE

You own the critical path no one else can shorten. The clinical advisor and the trademark are slow, external, and gate the others’ work — so they start in Week 1, today, before anything else on your list.

Your tasks, by sprint.

SPRINT 0  Lock & Unblock

WEEK 1   Start the slow things first.

| TASK | WHEN | DONE WHEN |
| --- | --- | --- |
| Open clinical advisor outreach — day 1 LONG POLE | Wk 1 | RD / eating-disorder-aware clinician candidates contacted; shortlist forming. Likely slower to land than the app is to build. |
| File the trademark BLOCKER | Wk 1 | HUNGER + FIG filed in apparel + software classes; the clearance read-back is calendared. |
| Draft + circulate the lane / decision-rights page ↳ All three sign | Wk 1 | One pager, signed by all three co-founders, pinned to the board. |
| Stand up the Trello board from the CSVs | Wk 1 | Board live; labels = lanes; the blockers are visible to everyone. |

SPRINT 1  Build & De-risk

WEEKS 2–4   Sign, protect, model.

| TASK | WHEN | DONE WHEN |
| --- | --- | --- |
| Sign the clinical advisor; brief on FIG + Guardian BLOCKER | Wk 2–4 | Contracted; has read the FIG prompt + Guardian spec and agreed the intake-floor parameters. |
| Lean legal: ToS, privacy, 17+, AI disclaimer | Wk 2–4 | Drafts in place; the AI-coach liability posture is documented. |
| Build the lightweight financial model ↳ FIG cost from Eng | Wk 3–4 | Unit economics at $6/mo Pro + a pre-raise burn figure modeled. |
| Choose beta logistics tooling | Wk 3 | TestFlight account + onboarding and feedback-capture tools selected. |
| Decide the creator-seed micro-run ↳ Brand’s list; name risk | Wk 3–4 | ~30–50 shirts ordered (founder-affordable) or consciously deferred, with the reason logged. |

SPRINT 2  Harden & Beta

WEEKS 5–7   Onboard, sign off, package the raise.

| TASK | WHEN | DONE WHEN |
| --- | --- | --- |
| Run beta logistics end-to-end | Wk 5–7 | 200 invited and onboarded smoothly; feedback captured. |
| Secure the clinical sign-off in writing HARD GATE ↳ Joint with Eng + advisor | Wk 5–6 | Advisor signs off, in writing, that FIG is safe to ship to external users. |
| Build the raise narrative + data-room v0 ↳ Traction (Brand) + retention (Eng) | Wk 7 | Retention, organic-CAC, and the traction story assembled for partners. |
| Draft the co-founder alignment pact | Wk 7 | The “ride the hostile press, don’t water it down” agreement drafted for signing before public launch. |

— YOUR WATCH-OUT The two slow things move silently. The advisor and the trademark are the only items on the whole board that you alone can unblock — and both run on external clocks you don’t control. Every day they’re not started, the beta date slips by a day, quietly, while everyone else feels productive. Start both in Week 1 and chase them weekly. They will be the reason we’re early or the reason we’re late.

Path cleared, story earned.

The build and the brand mean nothing if the path isn’t legal, safe, and fundable. That’s the lane.